## Sheet1
Project | Start Time | Completion days | person in charge
Project establishment | 2025-03-24 | 7 | Tao
Requirements collection | 2025-03-31 | 7 | Zhang
System architecture and database design | 2025-04-07 | 7 | Zhang
Backend development (LLM, multimodal processing) | 2025-04-14 | 14 | Hu
Front-end development (UI/UX, multi-platform adaptation) | 2025-04-28 | 14 | Huang
System Integration | 2025-05-12 | 7 | Tao
Unit Testing vs Integration Testing | 2025-05-19 | 4 | Hu
Performance and safety testing | 2025-05-23 | 4 | Huang
Final acceptance test (requirements traceback) | 2025-05-27 | 7 | Zhang
Deployment plan and environment preparation | 2025-06-03 | 3 | Tao
System launch and user training | 2025-06-06 | 3 | Hu
Online monitoring and problem solving | 2025-06-09 | 3 | Huang
Version planning and iteration preparation | 2025-06-12 | 3 | Zhang